PROJECT CHARTER

| Project Title | GreenWave Website |
| --- | --- |
| Project Sponsor | Temidayo Adeoye |
| Sponsor’s Organization | Stanix Consult |
| Project Manager | Patricia Chukwu |
| Start Date | 8th November 2025 |
| End Date | 6th December 2025 |

1. Problem Statement

In Nigeria, community-driven environmental efforts are often fragmented, undocumented, and lack visibility. Many volunteers, NGOs, schools, and community groups operate in isolation, making it difficult to track impact, inspire wider participation, or foster collaboration.

Furthermore, there is no centralized digital platform to connect, document, and amplify these efforts, limiting the potential for collective action and measurable positive environmental change.

1.1 Project Objectives

Objectives

- To design and develop an engaging and responsive web-based platform accessible across computers, tablets, and phones which serves as an educational and collaborative platform for environmental awareness.

- To raise awareness about environmental protection and practical steps towards sustainable living while connecting eco-volunteers and partner organizations through interactive features and campaigns.

- To engage individual and group action through storytelling, “eco quests,” and volunteer mobilization.

- To support global goals (SDGs 4, 11, 12, 13, 15, 17) that promote quality education, sustainable cities and communities, responsible consumption and production, climate action, life on land and partnership for the goals.

- To build a community of change-makers who collaborate on sustainable projects like tree planting, recycling, and climate advocacy with effective communication and feedback between users, volunteers, and partner organizations through chat features(WhatsApp) and contact forms.

- To ensure the platform is tested by 10 community volunteers, private organizations and general public users, reviewed and launched as a minimum viable product (MVP) for Stanix Consult within a 4-week timeline.

2. Scope Statement

GreenWave empowers community volunteers, eco-activists, and the general public to access practical steps for promoting and documenting sustainable habits such as recycling, tree planting, and climate advocacy.

Through a responsive digital hub, GreenWave provides resources and tools for education, storytelling, and engagement: creating a “wave” of collective environmental actions that inspire behavioral change, foster collaboration, and build a cleaner, greener, and more sustainable world.

The project will adopt a WAGILE methodology, tactically blending the structured planning of the Waterfall approach with the flexibility of Agile sprints. This ensures well-defined milestones and documentation while maintaining adaptability to user feedback, iterative design improvements, and stakeholder insights throughout development.

2.1 In Scope

- Landing Page

- About Us Page

- Eco Quest Page

- Engagement tools (blog and storytelling section, newsletter signup).

- Connect with us page

- Responsive design for all devices(Desktop,Tablet,Mobile)

- Floating Whatsapp Icon

- About page in alignment to SDG

2.2 Out of Scope

- Mobile app development .

- Advanced AI features like personalized recommendations

- E-commerce for eco-products.

- Full global localization beyond English.

- Multi-Language support

- Offline campaign management

- Paid Advertising or Marketing Campaign

2.3 Success Criteria

- MVP completed in 4 weeks

- A fully responsive web based platform accessible across computers , tablets and phone .

- Engagement partnership formed with environmental and sustainability organizations

- Minimum of 500 visitors within the first 3months of launch.

- Positive feedback from 80% of surveyed users on usability and relevance.

- Document at least 20 community initiatives that have been verified and recorded within the initial 6-month period.

3. Key Stakeholders

The key stakeholders for this project are:

- Project Manager – Greenwave Project Team

- Product Manager – Bruno and Arinola

- Software Developer – Bukola Laniyan and Samuel Ezechukwu

- QA Tester – Judith and Anuoluwa

4. High-level Timeline

Timeline: 4 Weeks

| S/N | Milestones/Phases | Estimated Duration |
| --- | --- | --- |
| 1 | Project Initiation and Documentation | 2days (Nov 8th - 9th) |
| 2 | Sprint 1 – Design & Documentation | 10th – 15th Nov |
| 3 | Sprint 2 – Development & Testing | 16th – 22nd Nov |
| 4 | Sprint 3 – Development & QA | 23rd Nov – 29th Nov |
| 5 | Sprint 4 – UAT, Closure & Graduation Prep | 30th – 6th Dec |
| 6 | Project Showcase: YouTube Live | 13th December 2025 |

5. Major Risks, Assumptions, and Constraints

The risks and assumptions associated with this project are:

| Risks | Assumptions | Constraints |
| --- | --- | --- |
| Delay in task completion | All team members are available throughout the 4-week project period. | Fixed 4-week timeline with no extension. |
| Deployment or hosting failure | Hosting, domain, and GitHub access are ready before Sprint 1. | Limited budget for additional tools or integrations. |
| Low stakeholder engagement | Stakeholders will be available for weekly review and approval. | Daily Standups and sprint reviews restricted to WAT time zone coordination |

6. Approval and Sign-off

| Stakeholder Name | Title | Signature | Date |
| --- | --- | --- | --- |
| Temidayo Adeoye | Project Sponsor |  | 15/11/2025 |
| Olamide Akinpelu | Program Manager |  | 15/11/2025 |
| Greenwave Project team | Project Manager |  | 15/11/2025 |